## Sheet1
Work Breakdown | [7 empty] | Status values: | Priority values
Category | Work Item | Status | Priority | Cost (hrs) | Cost (actual) | Start Date | End Date | Active | 1
A-Planning | Introduction to the IA project | Done, tested | 2 | 1 | 1 | 2015-01-12 | 2015-01-12 | Cut | 2
A-Planning | The Paragraph-Consultation with Advisor and goals | Done, tested | 3 | 1 | 0.75 | 1/14,15,16/2015 | 2015-01-26 | Done, not tested | 3
B | Consultation with Client and Advisory | Done, tested | 3 | 1 | 1 | 2015-01-27 | 2015-01-27 | Done, tested
B | Layout of the app (screens and pages) | Done, tested | 1 | 0.5 | 0.5 | 2015-01-29 | 2015-01-29
B | Research into Android Studio (how to use it) | Done, tested | 3 | 3 | 3 | 2015-02-04 | 2015-02-06
C | Making the start screen | Done, tested | 2 | 1900-01-01 | 2 | 2015-02-08 | 2015-02-10
C | Creating buttons to switch between pages | Done, tested | 2 | 2 | 6 | 2015-02-10 | 2015-02-14
C | Create textfields for user input | Done, tested | 2 | 1 | 1 | 2015-02-14 | 2015-02-14
C | Creating save button with toast | Done, tested | 3 | 0.5 | 0.5 | 2015-02-14 | 2015-02-14
B | Research into various databases | Done, not tested | 1 | 1 | 0.5 | 2015-02-20 | 2015-02-20
C | Creation of Shared Preference database | Cut | 3 | 5 | 5 | 2015-02-21 | 2015-02-21
C | Creation of SQLite database | Done, tested | 3 | 12 | 12 | 2015-02-22 | 2015-02-22
C | Displaying data into textfields | Done, tested | 3 |  |  | 2015-02-28 | 2015-03-01
C | Edit background and visuals of each page | Done, tested | 1 | 2 | 1.5 | 2015-03-01 | 2015-03-01
D | Talk with advisor to demonstrate project | Done, tested | 3 | 0.5 | 0.5 | 2015-03-02 | 2015-03-02
E | Get feedback about the program | Done, tested | 3 | 0.5 | 0.5 | 2015-03-02 | 2015-03-02